## Project Plan
- | Task Title | Parent Task/Category | Description | Priority | Status | Start Date | End Date | Total Time | Link (GitHub)
| Create Project Team | Planning | The team will be assembled for a project. | High | Complete | 2021-09-08 | 2021-09-17 | 216 hours (9 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226511
| Propose Project | Planning | The team has decided on a project and will propose it. | High | Complete | 2021-09-24 | 2021-09-27 | 72 hours (3 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70227059
| Project Approved | Planning | The project has been approved and will move forward. | High | Complete | 2021-09-27 | 2021-09-29 | 48 hours (2 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70227054
| Assign Team Roles | Planning | Team roles will be assigned to better organize what occurs during the development of our project. | Normal | Complete | 2021-09-29 | 2021-10-08 | 216 hours (9 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70227044
| Create The Project Plan | Planning | The project plan will be created for future objectives. | High | Complete | 2021-09-29 | 2021-10-08 | 216 hours (9 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70227038
| Project Plan Peer Review | Planning | Each team member will give construct feedback about their peers regarding their work on the Project Plan. | Low | Complete | 2021-10-06 | 2021-10-08 | 48 hours (2 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70227121
| Determine Project Requirements | Analysis | More specific requirements for the application will be discussed. | High | Active | 2021-10-08 | 2021-10-22 | 336 hours (14 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70227008
| Project Requirements Peer Review | Analysis | Each team member will give construct feedback about their peers regarding their work on gathering project requirements. | Low | Upcoming | 2021-10-20 | 2021-10-22 | 48 hours (2 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70227020
| High-Level Design | Design | A high-level view of the project architecture will be established and formalized. | Normal | Upcoming | 2021-10-22 | 2021-11-05 | 336 hours (14 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226982
| Low-Level Design | Design | The categories broken down in the high-level view will further be broken down and detailed to assist in the coding process. | Normal | Upcoming | 2021-10-22 | 2021-11-05 | 336 hours (14 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226940
| Design Peer Review | Design | Each team member will give construct feedback about their peers regarding their work on the design phase. | Low | Upcoming | 2021-11-03 | 2021-11-05 | 48 hours (2 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226928
| Establish Version Control System | Implementation | A GitHub repository will be created and initial commitments will be made for the project. | High | Upcoming | 2021-11-05 | 2021-11-07 | 48 hours (2 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226873
| Create Testing Environment | Implementation | A setup of software and hardware will be created that will allow us to begin developing the application. | High | Upcoming | 2021-11-05 | 2021-11-07 | 48 hours (2 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226861
| Implement Data Level Logic | Implementation | The team will begin working on the logic that will drive the application itself. | Normal | Upcoming | 2021-11-08 | 2021-11-22 | 336 hours (14 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226848
| Implement User Interface | Implementation | The team will begin working on the main user interface and any sub user interfaces that will exist. | Normal | Upcoming | 2021-11-08 | 2021-11-22 | 336 hours (14 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226832
| User Interface Testing | Testing | The team will begin testing and debugging the user interfaces of the application. | Normal | Upcoming | 2021-11-23 | 2021-11-30 | 168 hours (7 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226804
| Data Logic Testing | Testing | The team will begin testing and debugging the internal logic of the application. | Normal | Upcoming | 2021-11-23 | 2021-11-30 | 168 hours (7 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226779
| System Updates | Maintenance | The team will maintain the system through updates to the application. | Normal | Upcoming | 2021-12-01 | 2021-12-12 | 264 hours (11 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226760
| Discuss Lessons Learned | Wrap-Up | Mistakes and things that went well will be reviewed, and team members will reflect on how the project went. | Normal | Upcoming | 2021-12-06 | 2021-12-12 | 144 hours (6 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226679
| Final Peer Review | Wrap-Up | Each team member will give construct feedback about their peers regarding their work on the project as a whole. | Low | Upcoming | 2021-12-10 | 2021-12-12 | 48 hours (2 days) | https://github.com/carsonkoball/ProfessionalInventoryManager/projects/1#card-70226724
| TEAM ROLES |  |  | Priority Key | Status Key
| Project Manager: Carson Koball (Manages the project at the head of the team while working through all stages of development.) |  |  | Low: Lowest Priority | Upcoming: Future, To-Do Task
| Analyst: Carson Koball (Evaluates previous and current user data, similar applications, etc. and improves and guides the project using these statistics.) |  |  | Normal: Average Priority | Active: Current Task
| Technical Lead: Daniel Holmstrom (Manages team in the project's design, coding, architecture, etc. and verifies the technical quality of the project.) |  |  | High: Extereme Priority | Complete: Past, Finished Task
User Representative: Daniel Holmstrom (Represents the user needs and ideas for the project, while also being buffer between end users and project team.)
Executive Sponsor: Josie Johnson(Has big decision-making power, gives guidance and support to teams, and handles project resources.)
Tester: Josie Johnson (Tests and evaluates the application for discrepancies, possible user error, coding bugs, etc., while verifying that the specified requirements are met by the project throughout the development.)
Programmer(s): Carson Koball, Daniel Holmstrom, Josie Johnson (Team of programmers who will engineer the software and code for the project.)